## sheet1
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | UX Design: Basic user interface design with anticipated inputs and outputs required. | System Architecture: Overall system architecture with all known inputs and corresponding outputs. | Test User Interface: Test benches built into code base to help test outside module's inputs and outputs. | Personas: Personas created for end user perspective to aid in designing the system.
Iteration 1
UX Design | Week 3: UX Design
System Architecture | Week 2: System Architecture
Test User Interface | Week 2: Test User Interface | Software Requirement Specification: Document listing all software requirements for system to function as designed. | Project Schedule: Complete schedule outlining the plan for completing the project. | Coding Standards: Document listing the programing standards used in the development of the system. | Personas: Personas created for end user perspective to aid in designing the system. | UX Architecture: The underlying architecture for the user experience / user interface of the system. | Risk Assesment: Document detailing the risks involved in the completion of this project.
Personas | Week 3: Personas
Work Package 1
Software Requirement Specification | Week 3: SRS
Project Scedule | Week 2: Schedule | Class Diagrams: Diagrams outlining classes and their general structure, with attributes and functions. | Sequence Diagrams: Diagrams that demonstrate the suquence of the program. | Use Case Diagrams: Diagrams to demonstrate all inputs and outputs of the system with the corresponding actors for each. | Use Case Descriptions: Descriptions for each use case on the use case diagram. | Software Architecture: Overall architecture of the software showing the interactions between modules. | Test Plan: Document providing a plan to test the system and the test cases defined. | Iteration 2: Meeting with stakeholders showcasing the second iteration of the system / sub-system design. | Sub-System User Interface: Design of the user interface for the sub-system, on each module. | Interaction Diagrams: Diagrams listing the interactions of each module with it's connected modules.
Coding Standards | Week 3: Coding Standards
Personas | Week 3: Personas
UX Architectrure | Week 2: UX Architecture
Risk Assesment | Week 2: Risk Assesment | Integration: Integrating with other modules to begin assembling final system. | Sub-System Systemwide Test: Systemwide test after integration to check for proper communication between each module. | Sub-System Module Test: Test to ensure each module works as designed under specifications. | Dispatch Train to Dest: Test systems capability to dispatch a train safely from the yard to a specified destination. | UI Input/Output Test: Test preformed with the UI
WorkPackage 2
Class Diagrams | Week 4: Class Diagrams
Sequence Diagrams | Week 5: Sequence Diagrams
Use Case Diagrams | Week 6: Use Case Diagrams | Iteration 4: Complete "Working" system with the ability to run multiple trains on multiple lines | Configuration Managment: Specifications on how to maintain the system, and preform maintanence. | Bug Reports: Bugs reported by fellow group members, or stake holders, and assigned accordingly. | Bugs Resolved: Reported bugs handled and patched for each module. | Installation guide: Document detailing the installation process for each module and other related information regarding the installation of the system. | Code Base: Entire basis of code for each module, which contains all source code and logic that the system runs from. | Test Plan: All tests completed from the plan and assigned pass/fail. Failures adressed accordingly. | Final Sub-System Test: Final test of the entire sub-system, to ensure proper functionality, and safe operation.
Use Case Descriptions | Week 7: Use Case Descriptions
Software Architecture | Week 3: Software Architecture
Test Plan | Week 3: Test Plan; Week 7: Test Plan
Iteration 2 | Week 5: Iteration2
Sub-System User Interface | Week 6: Sub-System UI
Interaction Diagrams | Week 7: Interaction Diagrams
Iteration 3
Integration | Week 8: Integration
Sub-System Systemwide Test | Week 10: Sub-System SW Test
Sub-System Module Test | Week 9: Sub-System M Test
Dispatach Train to Dest | Week 11: DTD
UI Input/Output Tests | Week 8: UI I/O Tests
Work Package 3
Iteration 4 | Week 14: Iteration4
Configuration Management | Week 2: CM; Week 13: Configuration Management
Bug Reports | Week 13: Bug Reports
Bugs Resolved | Week 14: Bugs Resolved
Installation Guide | Week 16: Install Guide
Code Base | Week 4: Code Base
Test Plan | Week 15: Test Plan
Final Sub-System Test | Week 16: FSST