## Alex
Risk | Frequency | Severity | Mitigation | Type
A module couldn't be finished due to time restrictions and the team member responsible notifies the group ahead of time | Probable | Serious | All available member try to help out with the module | Group Interaction
A team member fails to complete their assigned module with no notice to the group | Improbable | Critical | Will have to test the system individually | Group Interaction
A member consistently fails to show up to meetings | Probable | Serious | Talk to the member in question and get a schedule that works for them | Group Interaction
Non-functional requirements are redefined by the user | Occasional | Critical | Ensure that the requirements are defined clearly by both parties | Technical
Functional requirements are redefined by the user - programming | Occasional | Critical | Rewrite and reuse old code to be able to meet new programming requirements | Technical
Member of the group can no longer be apart of the project | Improbable | Catastrophic | Contact TA and professor to be able to drop a module and notify them | Group Interaction
All members are busy for the week and a meeting is unable to be scheduled | Probable | Serious | Increase communication between members during the week whenever possible | Group Interaction
Github isn't backed up correctly and all progress since last back up is lost | Occasional | Catastrophic | Try to find any backups or residue of the new code. Set up a good habit of updating Github | Technical
The project repository is unaccessable to all group members | Improbable | Catastrophic | Have one group member keep the code on laptop | Technical
Laptop Crashes and loses progress | Probable | Serious | Keep progress merged with Github | Technical
Laptop breaks and is inaccessible | Improbable | Catastrophic | Keep backup of files (ie Github) and use a loaner laptop in the meantime | Technical

## Justin
Risk | Frequency | Severity | Mitigation | Type
One or more team members are unable to complete a task by a group specified deadline. | High | Low | The team will agree upon a new deadline and complete the task by then | Schedule & Group Interaction
One or more team members are unable to complete a task by a class specified deadline. | Low | High | The team will ensure that all hard deadlines are met | Schedule & Group Interaction
One or more team members fail to attend class, lab, or a group meeting | High | Low | The team members in question will be caught up when the group next meets | Schedule & Group Interaction
A group member consistently fails to attend class, labs, and/or meetings | Low | Medium | The team members will reach out to the group member individually | Schedule & Group Interaction
The functional requirements set by the team change | High | Medium | The team will bring the functional requirements into question and fix them accordingly | Technical
The non-functional requirements set by the team change | Medium | Low | The team will bring the non-functional requirements into question and fix them accordingly | Technical
Any other project requirement set by the team changes | Low | Variable | The team will bring the requirements into question and fix them accordingly | Technical
A group member can no longer be a part of the team | Low | High | The team will reassign roles to ensure all necessary roles are filled | Schedule & Group Interaction
The team is unable to resolve a defect within an exceptable amount of time | Medium | Medium | If a defect takes too long to resolve, the members involved will take a break for 1-2 hours and come back to it later | Technical
Several team members are unavailabe to meet or work for an extend period (i.e. ECE 1195 lab is due) | Low | High | The remaining team members will complete their portions and make templates to help streamline work for preoccupied team members | Schedule & Group Interaction

## Cameron
Risk | Frequency | Severity | Mitigation | Type
A module couldn't be finished due to time restrictions and the team member responsible notifies the group ahead of time | Probable | Serious | All available member try to help out with the module | Group Interaction
A team member fails to complete their assigned module with no notice to the group | Improbable | Critical | Will have to test the system individually | Group Interaction
A member consistently fails to show up to meetings | Probable | Serious | Talk to the member in question and get a schedule that works for them | Group Interaction
Non-functional requirements are redefined by the user | Occasional | Critical | Ensure that the requirements are defined clearly by both parties | Technical
Functional requirements are redefined by the user - programming | Occasional | Critical | Rewrite and reuse old code to be able to meet new programming requirements | Technical
Member of the group can no longer be apart of the project | Improbable | Catastrophic | Contact TA and professor to be able to drop a module and notify them | Group Interaction
All members are busy for the week and a meeting is unable to be scheduled | Probable | Serious | Increase communication between members during the week whenever possible | Group Interaction
Github isn't backed up correctly and all progress since last back up is lost | Occasional | Catastrophic | Try to find any backups or residue of the new code. Set up a good habit of updating Github | Technical
The project repository is unaccessable to all group members | Improbable | Catastrophic | Have one group member keep the code on laptop | Technical
Hardware has trouble interacting with rest of module | Probable | Catastrophic | Test every change before implimenting | Technical

## Kyle
Risk Assessment
Kyle Kessler - Track Module
Risk | Frequency | Severity | Mitigation | Type
A module couldn't be finished due to time restrictions and the team member responsible notifies the group ahead of time | Probable | Serious | All available member try to help out with the module | Group Interaction
A team member fails to complete their assigned module with no notice to the group | Improbable | Critical | Will have to test the system individually | Group Interaction
A member consistently fails to show up to meetings | Probable | Serious | Talk to the member in question and get a schedule that works for them | Group Interaction
Non-functional requirements are redefined by the user | Occasional | Critical | Ensure that the requirements are defined clearly by both parties | Technical
Functional requirements are redefined by the user - programming | Occasional | Critical | Rewrite and reuse old code to be able to meet new programming requirements | Technical
Member of the group can no longer be apart of the project | Improbable | Catastrophic | Contact TA and professor to be able to drop a module and notify them | Group Interaction
All members are busy for the week and a meeting is unable to be scheduled | Probable | Serious | Increase communication between members during the week whenever possible | Group Interaction
Github isn't backed up correctly and all progress since last back up is lost | Occasional | Catastrophic | Try to find any backups or residue of the new code. Set up a good habit of updating Github | Technical
The project repository is unaccessable to all group members | Improbable | Catastrophic | Have one group member keep the code on laptop | Technical

## Yuheng
Risk Assessment
Module - CTC
Frequency | Improbable | Occasional | Probable | Type
A member consistently fails to show up to meetings | Probable | Serious | Talk to the member in question and get a schedule that works for them | Group Interaction
Non-functional requirements are redefined by the user | Occasional | Critical | Ensure that the requirements are defined clearly by both parties | Technical
Functional requirements are redefined by the user - programming | Occasional | Critical | Rewrite and reuse old code to be able to meet new programming requirements | Technical
Member of the group can no longer be apart of the project | Improbable | Catastrophic | Contact TA and professor to be able to drop a module and notify them | Group Interaction
All members are busy for the week and a meeting is unable to be scheduled | Probable | Serious | Increase communication between members during the week whenever possible | Group Interaction
Github isn't backed up correctly and all progress since last back up is lost | Occasional | Catastrophic | Try to find any backups or residue of the new code. Set up a good habit of updating Github | Technical
The project repository is unaccessable to all group members | Improbable | Catastrophic | Have one group member keep the code on laptop | Technical
Microphone isn't working and I am unable to participate in weekly meetings | Improbable | Serious | Try to join the meeting on another device that has a functioning microphone | Group Interaction
Laptop breaks and I am unable to code anymore | Improbable | Catastrophic | Find a laptop to use for now and code with that device | Technical
Laptop shuts down due to it being out of battery before I am able to save my code | Occasional | Serious | Upload and save your progress to GitHub next time | Technical

## Yun
Risk Assessment
Module - Train Controller
Frequency | Improbable | Occasional | Probable
Severity | Serious | Critical | Catastrophic
Risk | Frequency | Severity | Mitigation | Type
A module couldn't be finished due to time restrictions and the team member responsible notifies the group ahead of time | Probable | Serious | All available member try to help out with the module | Group Interaction
A team member fails to complete their assigned module with no notice to the group | Improbable | Critical | Will have to test the system individually | Group Interaction
A member consistently fails to show up to meetings | Probable | Serious | Talk to the member in question and get a schedule that works for them | Group Interaction
Non-functional requirements are redefined by the user | Occasional | Critical | Ensure that the requirements are defined clearly by both parties | Technical
Functional requirements are redefined by the user - programming | Occasional | Critical | Rewrite and reuse old code to be able to meet new programming requirements | Technical
Member of the group can no longer be apart of the project | Improbable | Catastrophic | Contact TA and professor to be able to drop a module and notify them | Group Interaction
All members are busy for the week and a meeting is unable to be scheduled | Probable | Serious | Increase communication between members during the week whenever possible | Group Interaction
Github isn't backed up correctly and all progress since last back up is lost | Occasional | Catastrophic | Try to find any backups or residue of the new code. Set up a good habit of updating Github | Technical
The project repository is unaccessable to all group members | Improbable | Catastrophic | Have one group member keep the code on laptop | Technical